## JobStatus
Cost |  | Budget | Completion | Actual | Committed | Forecast | Variance
Category | Description | Cost | % | Cost | Cost | Cost | %
0 | ***CLICK JobCOST>Clear Worksheet MENU TO CLEAR DEMO ENTRIES
1 | *** SAMPLE ENTRIES FOR DEMO | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
11 | Excavation, sitework | 2725.00 | 100.00 | 2300.00 | 2300.00 | 2300.00 | -15.60
12 | Foundations, floor slab | 6725.00 | 100.00 | 7200.00 | 7600.00 | 7600.00 | 13.01
13 | Flatwork, walkways, driveway | 3650.00 | 20.00 | 300.00 | 500.00 | 2500.00 | -31.51
13 | Flatwork, entry | 2250
15-PA | Painting | 4200.00 | 10.00 | 310.00 | 310.00 | 3100.00 | -26.19
17 | Finish hardware | 675.00 | 30.00 | 225.00 | 225.00 | 750.00 | 11.11
18-SHOW | Shower and tub, enclosures | 875.00 | 30.00 | 250.00 | 250.00 | 833.33 | -4.76
24-INT | Interior finishes | 5125.00 | 0.00 | 0.00 | 0.00 | 5125.00 | 0.00
28-WI | Wiring | 4500.00 | 20.00 | 0.00 | 700.00 | 3500.00 | -22.22
44 | Final cleanup | 750.00 | 0.00 | 0.00 | 0.00 | 750.00 | 0.00

## InputLog
Input | Cost |  | Budget | Completion | Actual | Committed
Date | Category | Description | Cost | % | Cost | Cost

## QuickHelp
QUICK HELP
How can I contact CPR International, Inc, the developer of this software? | To know more about CPR International, Inc. and other construction software please visit www.cprsoft.com. Other products: HomeCOST Estimator, GeneralCOST Estimator, RemodelCOST Estimator, RepairCOST Estimator, PaintCOST Estimator.
When I open JobCOST Controller, why does a menu called "JobCOST" appear in Excel's menu bar? | In order to make our system as easy to use as possible, we added functions to the familiar existing interface, namely the Excel menu bar. The JobCOST menu item shall be there *only* when you are using the JobCOST Controller. When you leave, it will disappear.
How do I start a new job? | Click on "Add New Cost Account" from Excel's JobCOST menu. Then start entering your jobcost account definitions. Add category (max 8 characters), description (max 50 characters). This will be the account for tracking costs. Note: We provide a sample jobcost file for a typical home construction. If your project is similar, edit this file using "Maintain Cost Account" function. Otherwise, use "Clear Worksheets" to start fresh.
How do I maintain accounts? | Periodically, you should maintain accounts to update expenses, committments, etc. First, place your mouse on the row and select "Maintain Cost Account" from Excel's JobCOST menu. Then start entering your jobcost account data. If Budget has changed (perhaps due to change orders), enter change in Budget Cost in the "Change This Period" column. If you have already started a job and expended funds, then also enter "Completion", "Actual Cost" and "Committed Cost".
What is Budget Cost? | Budget Cost is the basis for tracking costs. It usually originates from your estimate. Budget Cost does not change throughout the project unless scope of work changes, e.g. a change order that adds to scope of work.
What is Actual Cost? | Actual Cost is the expended funds for the jobcost item. This figure comes from accounting records.
What is Committed Cost? | Committed Cost is the amount that you are obliged to pay but have not yet paid, e.g. Work done by a subcontractor but not yet invoiced or paid.
What is Completion? | Completion is the percentage of physical completion of the jobcost item at the time of maintaining the JobCOST Controller file. For example, if you have 400 Lf of chain link fence to build and you have built 100 Lf in this period, then you enter 25% for completion in this period.
What is Forecast at Completion? | This is the amount that JobCOST Controller forecasts to be the total cost to complete the work item 100%. It is derived using your input as well as JobCOST Controller's intelligent algorithms.
What is Variance? | Variance is the forecasted difference from budget at job completion. This value can be positive (over budget) or negative (under budget).
How should I save my job setup? | After setting up a jobcost file the first time, save the file under a different name. Use Excel's File > Save As function. From then on, open this saved file for item maintenance.
What is JobStatus worksheet? | JobCOST Controller lists all jobcost entries in the JobStatus worksheet. *Note*: JobCOST Controller maintains this worksheet automatically. Therefore, do not edit or delete rows and columns from this worksheet directly. This may cause errors.
I can't directly add or edit the JobStatus workshet. Why? | Because JobStatus worksheet is protected for edits. Use JobCOST menu items to maintain this sheet. If you must unprotect this sheet, use Tools > Protection > Unprotect Sheet function from Excel menu. No password is required. We recommend to keep this sheet protected at all times.
What is InputLog worksheet? | JobCOST Controller lists each and every jobcost entry in the InputLog worksheet for audit trail. *Note*: JobCOST Controller maintains this worksheet automatically. Therefore, do not edit and modify this worksheet directly.
When should I use Clear Worksheets function from JobCOST menu? | When you start a new jobcost file and save it in a different name, you may want to clear the Jobcost.xls file worksheets to be ready to start another jobcost file when needed.
After entering I decided not to have the entry as a jobcost item. How can I delete a row from JobStatus worksheet. | Click on the row. Then click on "Delete Row/Cost Account" from JobCOST menu. You may not delete a row using Excel's delete function since the worksheet is protected.
How can I get Help? | Click on "Show JobCOST Help" from Excel's JobCOST menu. You can also email CPR International, Inc. at cpr@cprsoft.com for your questions.
How do I create jobcost reports? | Select "Create Summary Report" or "Create Detail Report" from the JobCOST menu.
Why did the report appear in a different Excel file? | JobCOST Controller creates the reports in a new Excel file so that you can save the report in a different name.
How do I save the jobcost report? | Simply use Excel's File > Save As function.
Can I add rows and edit the jobcost reports? | Yes, you can modify the jobcost reports.
How can I print a jobcost report? | Simply use Excel's File > Print function.
After the jobcost report is created, how can I go back to JobCOST Controller job file? | Click on the minimized jobcost file button from the Taskbar.
How can I enter my Authorization Code? | (For Trial edition of JobCOST Controller only) Click on the "Enter Authorization Code" button. Then enter the code provided. If you download a registered copy, you should not see this button because the system is already registered. However, if you have registered and still see the button, contact CPR International, Inc at cpr@cprsoft.com to receive your Authorization Code.
What happens when the trial period expires? | The system will cease to function. Even if you download the trial version again, it will not function.
How can I register online? | (For Trial version of JobCOST Controller only or to register additional copies) Click on "Register Online" submenu From Excel's JobCOST menu. Make sure that you have an Internet connection available. Using a credit card, make the payment and immediately download the registered edition from the Register Now site.
How can I register by mail? | (For Trial edition of JobCOST Controller only or to register additional copies) Click on the OrderForm tab to open the Order worksheet. Fill out, print and mail with a check or Money Order. When received, we will call or email your Authorization Code.
How can I get program updates and how much does it cost? | Visit our website at http://www.cprsoft.com and download the JobCOST Controller Trial version. When you open the program, enter the Authorization Code. This will activate JobCOST Controller as the registered version. You are entitled to lifetime free updates.
I'm using the Trial version successfully. Why should I pay to register JobCOST Controller anyway? | One reason is because it is only fair. If you receive value, why not make a fair payment. It will make you feel good. Other reasons are things like eliminating the time limitation, receiving free lifetime program updates, getting expert technical support from CPR international, Inc., creating a longlasting relationship with us as our priority customer, receiving discounts on CPR's other productivity programs.
How can I register feedback, report bugs, suggest improvements, request quote for multiple copies, seek affiliate relationship? | Email us at: cpr@cprsoft.com

## OrderForm
JobCOST Controller Order Form
First Name:
Last Name:
Company:
Address1:
Address2:
City:
State:
Zip:
Phone:
Fax:
Email:
Payment: | Qty | Cost | Total
Amount | 1 | 29 | 29
Sales Tax (CA orders)
S&H |  |  | 4.5
Total |  |  | 33.5
Payment By:
Check
Money Order
Mail To:
CPR International, Inc.
P.O. Box 6394
Folsom, CA 95763